## team estimate
time estimate
log in screen | 1 hr
create account screen | 15 mins (can mimick log in screen from the front end)
add account to user database | 30 mins
connect user to authentication | 1 hour
authentication page | no time because this will be all through 3rd party
search page | 1.5 hr
dates filter for search | 3hr
weather part for search | 2 hr
listing the options after search with prices | 5 hr
go back to search page to do a new search | 1 hr
click on certain destination to open google flights | 2 hr

## Marilyn
| front end | back end | time estimate
log in screen | design the layout | nothing until submit button is clicked | 1 hr
create account screen | design the layout | nothing until the submit button is clicked | 15 mins (can mimick log in screen from the front end)
add account to user database | nothing | need to take the users information and add it to the system | 30 mins
connect user to authentication | none | need to send user to page to set up an authentication method after they have created an account | 1 hour
authentication page | none | will probably be a 3rd parties page to do this | no time because this will be all through 3rd party
search page | design the looks of this with the 2 options they need to choose | nothing | 1.5 hr
dates filter for search | make it able to be chosen from a calendar starting from the current date | need to make this so that it only allows user to choose from current date and up to 2 years in advance max | 3hr
weather part for search | able to be chosen from multiple options - temperature, and or rain/snow/sun |  | 2 hr
listing the options after search with prices | layout of how each destination and flight price will be shown | use the weather and the weather api, and find places to travel that have that same weather. then need to connect to the google flights api and collect the flight prices to each destination to be displayed | 5 hr
go back to search page to do a new search | back button | able to clear and restart from the search page | 1 hr
click on certain destination to open google flights | allow a button placed to see flights | connect the button to the google flights where is has flight prices to that specific destination clicked on | 2 hr

## Wilbert
Part | Work
Frontend | Log in Screen
Frontend | Design of making account screen
Frontend | Making the parameter search input
Frontend | Making the template for showing the result
Backend | Showing the result from database to frontend
Backend | Setting up the frontend and backend langgguage connections such as flutter and firebase connections
Backend | Interactions of button that will move on to the next page
Backend | Making a code relation from backend to the databse
Database | Matching the parameter with the given database

## Gelila
task | frontend, backend, or data management? | time estimate
login/register page | frontend | 30 minutes
search screen (travel dates, preferred weather) | frontend | 1.5 hours
search results (filtering) | frontend | 1 hour
destination details on result page (include flight prices) | frontend | 2.5 hours
user authentication | backend | 1 hour
API integration (weather and flight prices) | backend | 1.5 hour
database schema for user accounts and saved trip details | data management | 1.5 hours
data storage system configuration | data management | 2 hours